## WBS
Project | Todo Application |  |  | Korn | Chokul | Created at | 2024-07-11 | Finished
[6 empty] | Updated at | 2024-07-11 | Working on
No. | Work | Schedule(date) |  | Actual days you took |  | Man-hours（hour） |  | Progress | Note
|  | Start | End | Start | End | Plan | Actual result
0 | Create Todo Application
0.1 | Create Client side | 2024-07-11 | 2024-07-23 |  |  | 64
0.1.1 | Write code of Login screen with HTML and CSS. | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-07-11 | 8 | 2 | 100%
0.1.2 | Write code of Register screen with HTML and CSS. | 2024-07-12 | 2024-07-12 | 2024-07-11 | 2024-07-11 | 8 | 2 | 100%
0.1.3 | Write code of Main screen with HTML and CSS. | 2024-07-15 | 2024-07-15 |  |  | 8
0.1.4 | Write code of Login screen's function with JavaScript. | 2024-07-16 | 2024-07-16 | 2024-07-11 | 2024-07-11 | 8 | 1 | 100%
0.1.5 | Write code of Register screen's function with JavaScript. | 2024-07-17 | 2024-07-17 | 2024-07-11 | 2024-07-11 | 8 | 1 | 100%
0.1.6 | Write code of Main screen's function with JavaScript. | 2024-07-18 | 2024-07-23 |  |  | 24
0.2 | Create Server side | 2024-07-24 | 2024-08-15 |  |  | 120
0.2.1 | Write User's Controller class | 2024-07-24 | 2024-07-24 |  |  | 8
0.2.2 | Write User's Request class | 2024-07-25 | 2024-07-25 |  |  | 8
0.2.3 | Write User's Model class | 2024-07-26 | 2024-07-26 |  |  | 8
0.2.4 | Write User's Service class | 2024-07-30 | 2024-07-30 |  |  | 8
0.2.5 | Write User's Repository class | 2024-07-31 | 2024-07-31 |  |  | 8
0.2.6 | Write User's Datasource class | 2024-08-01 | 2024-08-01 |  |  | 8
0.2.7 | Write Todo's Controller class | 2024-08-02 | 2024-08-05 |  |  | 16
0.2.8 | Write Todo's Request class | 2024-08-06 | 2024-08-06 |  |  | 8
0.2.9 | Write Todo's Model class | 2024-08-07 | 2024-08-07 |  |  | 8
0.2.10 | Write Todo's Service class | 2024-08-08 | 2024-08-08 |  |  | 8
0.2.11 | Write Todo's Repository class | 2024-08-09 | 2024-08-09 |  |  | 8
0.2.12 | Write Todo's Datasource class | 2024-08-13 | 2024-08-15 |  |  | 24
1 | Test Todo Application
1.1 | Write Sheet for the Test | 2024-08-16 | 2024-08-16 |  |  | 8
1.2 | Test | 2024-08-19 | 2024-08-21 |  |  | 24
2 | Deploy Todo Application
2.1 | Deploy Todo App to CentOS's Tomcat | 2024-08-22 | 2024-08-22 |  |  | 8

## How to write in WBS
Project | Todo Application |  |  | Writer of this sheet |  | Created at |  | Finished
[6 empty] | Updated at |  | Working on
No. | Work | Schedule(date) |  | Actual days you took |  | Man-hours（hour） |  | Progress | Note
|  | Start | End | Start | End | Plan | Actual result
0 | Create Todo Application
0.1 | Create Client side | 2024-07-11 | 2024-07-23 |  |  | 64
0.1.1 | Write code of Login screen with HTML and CSS. | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-07-11 | 8 | 8 | 100%
0.1.2 | Write code of Register screen with HTML and CSS. | 2024-07-12 | 2024-07-12 |  |  | 8
0.1.3 | Write code of Main screen with HTML and CSS. | 2024-07-15 | 2024-07-15 |  |  | 8
0.1.4 | Write code of Login screen's function with JavaScript. | 2024-07-16 | 2024-07-16 |  |  | 8
0.1.5 | Write code of Register screen's function with JavaScript. | 2024-07-17 | 2024-07-17 |  |  | 8
0.1.6 | Write code of Main screen's function with JavaScript. | 2024-07-18 | 2024-07-23 |  |  | 24
0.2 | Create Server side | 2024-07-24 | 2024-08-15 |  |  | 120
0.2.1 | Write User's Controller class | 2024-07-24 | 2024-07-24 |  |  | 8
0.2.2 | Write User's Request class | 2024-07-25 | 2024-07-25 |  |  | 8
0.2.3 | Write User's Model class | 2024-07-26 | 2024-07-26 |  |  | 8
0.2.4 | Write User's Service class | 2024-07-30 | 2024-07-30 |  |  | 8
0.2.5 | Write User's Repository class | 2024-07-31 | 2024-07-31 |  |  | 8
0.2.6 | Write User's Datasource class | 2024-08-01 | 2024-08-01 |  |  | 8
0.2.7 | Write Todo's Controller class | 2024-08-02 | 2024-08-05 |  |  | 16
0.2.8 | Write Todo's Request class | 2024-08-06 | 2024-08-06 |  |  | 8
0.2.9 | Write Todo's Model class | 2024-08-07 | 2024-08-07 |  |  | 8
0.2.10 | Write Todo's Service class | 2024-08-08 | 2024-08-08 |  |  | 8
0.2.11 | Write Todo's Repository class | 2024-08-09 | 2024-08-09 |  |  | 8
0.2.12 | Write Todo's Datasource class | 2024-08-13 | 2024-08-15 |  |  | 24
1 | Test Todo Application
1.1 | Write Sheet for the Test | 2024-08-16 | 2024-08-16 |  |  | 8
1.2 | Test | 2024-08-19 | 2024-08-21 |  |  | 24
2 | Deploy Todo Application
2.1 | Deploy Todo App to CentOS's Tomcat | 2024-08-22 | 2024-08-22 |  |  | 8
Write your name in here.
Write date that you started to get on any work and date that you finished the work in here.
Write time that you took to finish your work in here.
Write how much work progressed by percentage in here.